## Sheet1
APARTMENT MANGEMENT SYSTEM TIMELINES
sno. | Task Name | Start Date | End Date | No. of Hours | Buffer Hours | Buffer+product | Total Hours | Status | sno. | Task Name | Start Date | End Date | No. of Hours | Buffer Hours | Total Hours | Status
| Module:1 (UI/UX) | [5 empty] | 480
1 | User Panel UI/UX | 2024-04-22 | 2024-04-25 | 126 | 2 | 128 |  | Completed
2 | Website UI/UX | 2024-04-26 | 2024-04-26 | 31 | 1 | 32 |  | Completed
3 | Security UI/UX | 2024-04-29 | 2024-04-30 | 62 | 2 | 64 |  | Completed
4 | Society Admin UI/UX | 2024-01-05 | 2024-06-05 | 126 | 2 | 128 |  | Completed
5 | Super Admin UI/UX | 2024-07-05 | 2024-10-05 | 126 | 2 | 128 |  | Completed
|  |  |  | 471 | 9 |  | 480
Frontend | [8 empty] | Backend
| Module:2 (User Panel) | [5 empty] | 576 |  | 1 | Authentication (all) | 2024-05-13 | 2024-05-24 | 60 | 8 | 68 | Completed | Risk Forecasting In Back End
1 | Authentication | [8 empty] | Login |  |  | 10 | 2 | 12 | In Progress
| Splash Screen, Onboard Screen | 2024-05-20 | 2024-05-20 | 8 |  | 8 |  | Completed |  | SignUp | [5 empty] | In Progress
| Login, SignUp, Forgot Password | 2024-05-21 | 2024-05-21 | 30 | 2 | 32 |  | Completed |  | Forgot Password | [5 empty] | In Progress | Risk 1: Socket.io (Real-Time Communication)
2 | Home |  |  |  | 4 | 4 |  | Completed |  | Reset Password | [5 empty] | Completed
| Header, Bottom Tabs | 2024-05-22 | 2024-05-22 | 15 |  | 15 |  | Completed |  | SignOut | [5 empty] | Completed
| Quick Actions | 2024-05-22 | 2024-05-22 | 15 |  | 15 |  | Completed | 2 | Chat Feature(I/O Stream) | 2024-05-27 | 2024-06-07 | 72 | 8 | 80 | In Progress | Risk 2: Payments & Bills
| Recent Activities | 2024-05-22 | 2024-05-22 | 15 |  | 15 |  | Completed |  | Both Group and Individual | [5 empty] | In Progress
| Advertisements, Navigations | 2024-05-22 | 2024-05-22 | 15 |  | 15 |  | Completed |  | Create, Delete, Edit, Get | [5 empty] | In Progress
3 | Notifications | 2024-05-27 | 2024-05-27 | 22 | 2 | 24 |  | Completed | 3 | Payment Gateway | 2024-06-10 | 2024-06-21 | 64 | 16 | 80 | To Do | Risk 3: Panic Button
4 | Profile |  |  |  | 4 | 4 |  | Completed |  | Create API which links to real-time axis. | [5 empty] | To Do
| User Profile Details,Edit | 2024-05-27 | 2024-05-27 | 15 |  | 15 |  | Completed |  | (Legal permissions) | [5 empty] | To Do
| My Documents | 2024-05-27 | 2024-05-27 | 8 |  | 8 |  | Completed |  | Create, Delete, Edit, Get | [5 empty] | To Do
| Add Households | 2024-05-27 | 2024-05-27 | 15 |  | 15 |  | Completed | 4 | Payment Maintenance Calculation | 2024-06-24 | 2024-06-05 | 72 | 8 | 80 | To Do
| Settings | 2024-05-27 | 2024-05-27 | 22 |  | 22 |  | Completed |  | (this is for both the frontend and back-end) | [5 empty] | To Do
| Logout | 2024-05-28 | 2024-05-28 | 8 |  | 8 |  | Completed |  | Create, Delete, Edit, Get | [5 empty] | To Do | Risk Forecasting In Front End
5 | Community
| a. Discover |  |  |  | 2 | 2 |  | Completed
| Emergency Contact | 2024-05-28 | 2024-05-28 | 7 |  | 7 |  | Completed | 5 | Advertisements | 2024-05-13 | 2024-05-17 | 38 | 2 | 40 | Completed | Risk 1: Socket.io (Real-Time Communication)
| Local Directory | 2024-05-28 | 2024-05-28 | 8 |  | 8 |  | Completed |  | (Displaying Rent/Sale Flats ) | [5 empty] | Completed
| Residents | 2024-05-28 | 2024-05-28 | 7 |  | 7 |  | Completed |  | create, delete, edit. | [5 empty] | Completed
| Local Services | 2024-05-28 | 2024-05-28 | 8 |  | 8 |  | Completed | 6 | Notice Board | 2024-05-20 | 2024-05-24 | 40 | 0 | 40 | Completed | Risk 2: Payments & Billings
| b.Engage |  |  |  | 4 | 4 |  | Completed |  | Sharing information | [5 empty] | Completed
| Help Desk | 2024-05-29 | 2024-05-29 | 14 |  | 14 |  | Completed |  | Create, Delete, Edit, Get | [5 empty] | Completed
| Amenities | 2024-05-29 | 2024-05-29 | 8 |  | 8 |  | Completed | 7 | Polls | 2024-05-27 | 2024-05-31 | 39 | 1 | 40 | Completed | Risk 3: Panic Button
| Discussions | 2024-05-29 | 2024-05-29 | 24 |  | 24 |  | Completed |  | (In this some questions are created and by | [5 empty] | Completed
| Polls and Events | 2024-05-29 | 2024-05-29 | 16 |  | 16 |  | Completed |  | result should be displayed) | [5 empty] | Completed
| Documents | 2024-05-29 | 2024-05-29 | 8 |  | 8 |  | Completed |  | Create, Delete, Edit, Get | [5 empty] | Completed
| Notice Board | 2024-05-29 | 2024-05-29 | 12 |  | 12 |  | Completed | 8 | Events | 2024-06-03 | 2024-06-07 | 40 | 0 | 40 | Completed
| c. Society Bills | 2024-05-29 | 2024-05-30 | 14 | 2 | 16 |  | Completed |  | (special occasions are some activities in | [5 empty] | Completed
| d. My Bills |  |  |  | 2 | 2 |  | Completed |  | the community) | [5 empty] | Completed
| Payments | 2024-05-30 | 2024-05-30 | 30 |  | 30 |  | Completed |  | Create, Delete, Edit, Get | [5 empty] | Completed
| History | 2024-05-30 | 2024-05-30 | 16 |  | 16 |  | Completed | 9 | Number Code/QR Code Using Details | 2024-06-10 | 2024-06-14 | 38 | 2 | 40 | Completed
6 | Households |  |  |  | 4 | 4 |  | Completed |  | (For special permissions) | [5 empty] | Completed
| Add Flat | 2024-05-30 | 2024-05-30 | 12 |  | 12 |  | Completed |  | Create, Delete, Edit, Get | [5 empty] | Completed
| Add Family | 2024-05-30 | 2024-05-30 | 12 |  | 12 |  | Completed | 10 | Visitors Record | 2024-06-17 | 2024-07-21 | 38 | 2 | 40 | Completed
| Add Pets | 2024-05-31 | 2024-05-31 | 12 |  | 12 |  | Completed |  | (record of visitors all flats),Create, Delete, Edit, Get | [5 empty] | Completed
| Add Vehicles | 2024-05-31 | 2024-05-31 | 8 |  | 8 |  | Completed | 11 | SOS panic Button | 2024-06-24 | 2024-07-05 | 76 | 4 | 80 | To Do
| Add Vistors | 2024-05-31 | 2024-05-31 | 12 |  | 12 |  | Completed |  | Create,Stop | [5 empty] | To Do
| Frequent Entries & Validated Entries | 2024-05-31 | 2024-05-31 | 12 |  | 12 |  | Completed
| My Daily Help | 2024-05-31 | 2024-05-31 | 12 |  | 12 |  | Completed
7 | Activites |  |  |  | 2 | 2 |  | Completed | 12 | Profile/Documents | 2024-05-13 | 2024-05-17 | 38 | 2 | 40 | Completed
| Vistor Approval Request | 2024-05-24 | 2024-05-24 | 15 |  | 15 |  | Completed |  | For every panel (Owner, Tenant, | [5 empty] | Completed
| Find Domestic Help | 2024-05-24 | 2024-05-24 | 8 |  | 8 |  | Completed |  | Society-admin, Security, Super-admin.) | [5 empty] | Completed
| Manage Domestic Help | 2024-05-24 | 2024-05-24 | 15 |  | 15 |  | Completed |  | Create, Delete, Edit, Get | [5 empty] | Completed
| Manage Delivery | 2024-05-24 | 2024-05-24 | 8 |  | 8 |  | Completed | 13 | Amenities | 2024-05-20 | 2024-05-24 | 38 | 2 | 40 | Completed
8 | Quick Actions |  |  |  | 5 | 5 |  | Completed |  | Special access to pools, theater, halls etc., | [5 empty] | Completed
| Allow Future Entries | 2024-05-23 | 2024-05-23 | 15 |  | 15 |  | Completed |  | Based on the users limitations | [5 empty] | Completed
| Allow Exit | 2024-05-23 | 2024-05-23 | 8 |  | 8 |  | Completed |  | Create, Delete, Edit, Get | [5 empty] | Completed
| Notify Gate - Call and Message Security | 2024-05-23 | 2024-05-23 | 16 |  | 16 |  | Completed | 14 | Households | 2024-05-27 | 2024-05-31 | 39 | 1 | 40 | Completed
| My Visit - Request Visit Code | 2024-05-23 | 2024-05-23 | 8 |  | 8 |  | Completed |  | For every society, | [5 empty] | Completed
| SOS - Panic Button | 2024-05-23 | 2024-05-23 | 10 |  | 10 |  | Completed |  | (Flat, Family-members, Pets,Visitos, etc..,) | [5 empty] | Completed
|  |  |  | 543 | 33 |  |  |  |  | Create, Delete, Edit, Get | [5 empty] | Completed
[9 empty] | 15 | Local Services | 2024-06-03 | 2024-06-07 | 38 | 2 | 40 | Completed
| Module:3 (Security & Website) | [5 empty] | 424 |  |  | Household needs | [5 empty] | Completed
1 | Security Authentication | 2024-05-14 | 2024-05-14 | 60 | 4 | 64 |  | Completed |  | (Venders, Milk-men, Chief, Maids, | [5 empty] | Completed
2 | Entry Code | 2024-05-14 | 2024-05-14 | 60 | 4 | 64 |  | Completed |  | etc..,) Create, Delete, Edit, Get | [5 empty] | Completed
3 | Frequent Visitors | 2024-05-15 | 2024-05-15 | 60 | 4 | 64 |  | Completed | 16 | Inventory | 2024-06-10 | 2024-06-14 | 39 | 1 | 40 | Completed
4 | Visitors | [8 empty] | Appartment properties List | [5 empty] | Completed
| Inside Visitors | 2024-05-16 | 2024-05-16 | 30 | 2 | 32 |  | Completed |  | Chairs, Ladders, Tools, | [5 empty] | Completed
| Waiting Visitors | 2024-05-16 | 2024-05-16 | 30 | 2 | 32 |  | Completed |  | etc..,) Create, Delete, Edit, Get | [5 empty] | Completed
5 | More Section | [7 empty] | 17 | Quick Actions | 2024-06-17 | 2024-06-25 | 50 | 6 | 56 | Completed
| Add Visitors Details | 2024-05-17 | 2024-05-17 | 40 |  | 40 |  | Completed |  | (Residents giving Instructions to Security | [5 empty] | Completed
| List | 2024-05-17 | 2024-05-17 | 22 | 2 | 24 |  | Completed |  | about visitors, cabs, deliveries allow kids | [5 empty] | Completed
6 | Home Screen | [8 empty] | to exit etc.., by call, message, alert mode.) | [5 empty] | Completed
| Top Navigations | 2024-05-18 | 2024-05-18 | 15 | 1 | 16 |  | Completed |  | Create, Delete, Edit, Get | [5 empty] | Completed
| Bottom Navigations | 2024-05-18 | 2024-05-18 | 15 | 1 | 16 |  | Completed | 18 | Asserts | 2024-06-26 | 2024-06-28 | 23 | 1 | 24 | Completed
| Logout | 2024-05-18 | 2024-05-18 | 8 |  | 8 |  | Completed |  | (Each flat bill payments Community | [5 empty] | Completed
| Security Profile | 2024-05-18 | 2024-05-18 | 22 | 2 | 24 |  | Completed | 19 | Settings |  |  | 38 | 2 | 40 | To Do
8 | Website | 2024-05-20 | 2024-05-20 | 38 | 2 | 40 |  | Completed |  | for user having settings like stop notification, etc. | [5 empty] | To Do
|  |  |  | 400 | 24 |  |  |  |  | Create, Delete, Edit, Get | [5 empty] | To Do
| Module:4 (Society Admin) | [5 empty] | 856 |  | 20 | Fetching | 2024-07-08 | 2024-07-19 | 228 | 12 | 240 | To Do
1 | Authentication
| Login, SignUp, Forgot Password | 2024-06-03 | 2024-06-03 | 22 | 2 | 24 |  | Completed | [6 empty] | 1200
2 | Home
| Dashboard | 2024-06-04 | 2024-06-04 | 38 | 2 | 40 |  | Completed
| Analysis | 2024-06-04 | 2024-06-04 | 20 | 4 | 24 |  | Completed
3 | Society Management
| Pending Approvals | 2024-06-05 | 2024-06-05 | 22 | 2 | 24 |  | Completed
| Notice Board | 2024-06-05 | 2024-06-05 | 10 |  | 10 |  | Completed
| Management Community | 2024-06-05 | 2024-06-05 | 10 | 2 | 12 |  | Completed
| Emergency Contacts | 2024-06-05 | 2024-06-05 | 10 |  | 10 |  | Completed
| Manage Events | 2024-06-05 | 2024-06-06 | 20 |  | 20 |  | Completed
| Discussions and Polls | 2024-06-06 | 2024-06-06 | 38 | 2 | 40 |  | In Progress
| Document Repository | 2024-06-07 | 2024-06-07 | 23 | 1 | 24 |  | Completed
| Society Inspection | 2024-06-07 | 2024-06-07 | 20 | 4 | 24 |  | Completed
4 | Flat & Residents Management
| Manage Residents/Owners | 2024-06-07 | 2024-06-07 | 20 | 4 | 24 |  | Completed
| Manage Flats | 2024-06-07 | 2024-06-10 | 20 | 4 | 24 |  | Completed
| Change Ownership | 2024-06-10 | 2024-06-10 | 8 |  | 8 |  | Completed
| Move In-Out | 2024-06-10 | 2024-06-10 | 8 |  | 8 |  | Completed
| Move Tracker | 2024-06-10 | 2024-06-10 | 8 |  | 8 |  | Completed
| Rent Aggremenets | 2024-06-10 | 2024-06-10 | 8 |  | 8 |  | Completed
| Add Appartment | 2024-06-10 | 2024-06-11 | 20 | 2 | 22 |  | Completed
| Home Inspection | 2024-06-11 | 2024-06-11 | 20 | 2 | 22 |  | Completed
5 | Gate & Visitor Management
| Manage Staff/Security | 2024-06-11 | 2024-06-11 | 23 | 1 | 24 |  | Completed
| Manage Daily help | 2024-06-11 | 2024-06-12 | 18 | 2 | 20 |  | Completed
| In & Out Records | 2024-06-12 | 2024-06-12 | 18 | 2 | 20 |  | Completed
| Attendence | 2024-06-12 | 2024-06-12 | 8 |  | 8 |  | Completed
| Vehicle Entry/Exit Summary | 2024-06-12 | 2024-06-12 | 15 | 1 | 16 |  | Completed
6 | Inventory Management
| Add Inventory | 2024-06-12 | 2024-06-12 | 7 | 1 | 8 |  | Completed
| ManageInventory | 2024-06-13 | 2024-06-13 | 18 | 2 | 20 |  | Completed
| List the Inventory | 2024-06-13 | 2024-06-13 | 14 |  | 14 |  | Completed
| Track Inventory | 2024-06-13 | 2024-06-13 | 18 | 2 | 20 |  | Completed
| Inventory Bills | 2024-06-13 | 2024-06-14 | 18 | 2 | 20 |  | Completed
7 | Vendor Management
| Add Vendor | 2024-06-14 | 2024-06-14 | 8 |  | 8 |  | Completed
| Manage Vendor | 2024-06-14 | 2024-06-14 | 20 | 2 | 22 |  | Completed
| Add Vendor Bill | 2024-06-14 | 2024-06-14 | 10 |  | 10 |  | Completed
| Payment History | 2024-06-14 | 2024-06-17 | 18 | 2 | 20 |  | Completed
| Vendor Review | 2024-06-17 | 2024-06-17 | 8 |  | 8 |  | In Progress
8 | Amenities Management
| Add Aminity | 2024-06-17 | 2024-06-17 | 8 |  | 8 |  | Completed
| Manage Aminity | 2024-06-17 | 2024-06-17 | 22 | 2 | 24 |  | Completed
| Add Bills | 2024-06-17 | 2024-06-17 | 10 |  | 10 |  | Completed
| Payment Bills | 2024-06-17 | 2024-06-18 | 22 | 2 | 24 |  | Completed
| Mange Booking | 2024-06-18 | 2024-06-18 | 12 | 2 | 14 |  | Completed
| Aminities Review | 2024-06-18 | 2024-06-18 | 8 |  | 8 |  | To Do
9 | Help Desk | 2024-06-18 | 2024-06-19 | 31 | 1 | 32 |  | Completed
10 | Financial Management
| Billings | 2024-06-19 | 2024-06-19 | 22 | 1 | 23 |  | Completed
| Generate Bills | 2024-06-19 | 2024-06-19 | 15 | 2 | 17 |  | Completed
| Transactions | 2024-06-19 | 2024-06-20 | 23 | 1 | 24 |  | Completed
| Reports | 2024-06-20 | 2024-06-20 | 23 | 1 | 24 |  | Completed
11 | Account Setting | 2024-06-20 | 2024-06-20 | 13 | 1 | 14 |  | Completed
12 | Notifications | 2024-06-20 | 2024-06-20 | 18 | 2 | 20 |  | Completed
|  |  |  | 793 | 63
| Module: 5 (Super Admin) | [5 empty] | 704
1 | Authentication
| Login, SignUp, Forgot Password, Logout | 2024-06-21 | 2024-06-21 | 60 | 4 | 64 |  | To Do
2 | Home
| Dashboard | 2024-06-24 | 2024-06-24 | 60 | 4 | 64 |  | To Do
| Analysis | 2024-06-25 | 2024-06-25 | 60 | 4 | 64 |  | To Do
3 | Communities
| Add Community Logins | 2024-06-26 | 2024-06-26 | 30 | 2 | 32 |  | To Do
| List the Communities | 2024-06-26 | 2024-06-26 | 24 |  | 24 |  | To Do
| Details | 2024-06-26 | 2024-06-27 | 44 | 4 | 48 |  | To Do
| Complaints | 2024-06-27 | 2024-06-27 | 24 |  | 24 |  | To Do
| Notices | 2024-06-27 | 2024-06-28 | 16 |  | 16 |  | To Do
| Users | 2024-06-28 | 2024-06-28 | 20 | 4 | 24 |  | To Do
| Staff | 2024-06-28 | 2024-06-28 | 12 | 2 | 14 |  | To Do
4 | Payments
| Add Bills | 2024-06-28 | 2024-06-29 | 38 | 2 | 40 |  | To Do
| Delete | 2024-06-29 | 2024-06-29 | 16 |  | 16 |  | To Do
| Manage Payments | 2024-06-29 | 2024-07-01 | 50 | 2 | 52 |  | To Do
| Track Payments | 2024-07-01 | 2024-07-01 | 30 | 2 | 32 |  | To Do
5 | Help Desk | 2024-07-01 | 2024-07-02 | 32 |  | 32 |  | To Do
6 | Notifications | 2024-07-02 | 2024-07-03 | 32 |  | 32 |  | To Do
7 | Communication | 2024-07-03 | 2024-07-05 | 95 | 5 | 100 |  | To Do
8 | Plans | 2024-07-05 | 2024-07-05 | 24 | 2 | 26 |  | To Do
|  |  |  | 667 | 37
| Fetching (All Panels) | 2024-07-08 | 2024-07-19 | 630 | 10 | 640 | 640 | To Do
| Module: 6 (Testing & Hosting) | [5 empty] | 616
| Testing ( 6 Members) |  |  | 330 | 10 | 340 |  | To Do
| Hosting (5 Members) |  |  | 270 | 6 | 276 |  | To Do
|  |  |  | 600 | 16
Total Frontend Hours-3200 | [8 empty] | Total Backend Hours-1200
UI/UX Design- 480
Testing & Hosting-616
Total Hours-5496
Starting Date:22/04/2024 | [8 empty] | Ending Date: 30/07/2024
SUBMISSION DATE:31/07/2024
sno: | Task | Completed | In Progress | To Do
1 | UI/UX | 100 | 0 | 0
2 | Front-End | 56.25 | 1.5 | 42.25
3 | Back-End | 49 | 7.6667 | 43.3333
4 | Testing/Hosting | 0 | 0 | 100
5 | Over All Percentage | 52.1834 | 2.5473 | 45.2693 | 100